## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations and Prerequistes for doing the project |  |  |  | 3- Completed
|  | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration |  |  |  | 3- Completed
|  | 3 | Social Media Integration, Content Creation, Optimization |  |  |  | 3- Completed
|  | 4 | Sentiment Analysis, Slack Integration and deployment |  |  |  | 2- In Progress
Note on F1: ====== ID#AAABs4-wLUs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
L
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Foundations and Prerequistes for doing the project | 23rd Sep | 7th Oct | Pankaj Bhattacharjee | Gained Knowledge about fundamental of python programming for the project | Done |  | Introduction | Installed Python and jupyter notebook successfully | Understood Naming conventions in python | Learnt Datatypes and variables | Using Datatype and variables practiced some problem | Practiced basic fundamentals | Learnt Flow controls | Learnt strings and it's method | Revised previously concepts | Practice problem using string method | Revised string methods and python function | Practiced functions | Implementation of strings +slicing+function | Learnt function in depth
2 |  | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th Oct | 22nd Oct | Pankaj Bhattacharjee | Understoood Project and workflow | In Progress |  | Worked on practical OOP examples | Practiced importing multiple modules in a single program. | Focused on basic NLP pipeline structure. | Understood how to build NLP pipelines. | Learned to integrate spaCy with other Python libraries. | Understood project requirements and goals. | Shared my view on project architecture. | Worked hands-on with virtual environment setup. | Explored the Hugging Face Transformers library. | interaction session | practice the transformers use | revising oops concept | Revised NLP | API intregation with google sheet
3 |  | Social Media Integration,Content Creation,Optimization | 23ed oct | 6th Nov | Pankaj Bhattacharjee | Learned social media API integration and AI-based content generation through practical implementation. | In progress |  | Understood Twitter API integration | complete twiter integration | Understanding Linkedin and instagram | working on linkedin and instagram api | Learned API integration basics through interactive sessions. | Practiced API integration and tested sample codes. | Studied and implemented mock data generation techniques. | Created AI-generated content using LLM and Groq API. | Practiced using Google Sheet connector for data automation. | Learned fundamentals of Generative AI and Large Language Models (LLMs). | Practiced LLM concepts and integrated with Google Sheet connector | Revised LLM fundamentals through interactive | Genrate different content | Handson seassion
4 |  | Sentiment Analysis, Slack Integration and Deployment | 6th Nov | 20th Nov | Pankaj Bhattacharjee | Learned Sentiment Analysis, Slack Integration and deployment on streamlit | Done |  | Got the fundamentals of API | Studied concept of API | Revised API topic | Worked on Assignment | Interactive and engagement session | learned how to optimize content | Learned about Sentiment Analysis | Known about slack integration | Learned about A/B Testing | Revised the A/B Testing | Practice on Content optimization and sentiment Analysis | Understand about Project Workflow | Discussed about Project Presentation | Mock presentation Done
Note on D2: ====== ID#AAABs4-wLUI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs4-wLVM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs4-wLUM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint1 | Day 2 | Difficulty understanding full project requirements | Discussed with mentor; clarified scope and listed tasks
Sprint 2 | Day 4 | Ambiguity in project goals and workflow steps | Conducted a team brainstorming session and reviewed project objectives
Sprint 2 | Day 6 | Confusion regarding Agile templates | Organized a meeting where the mentor clarified all doubts
Sprint 2 | Day 7 | Difficulty identifying potential use cases due to incomplete information | Performed additional research and consulted online resources to fill gaps
Sprint 2 | Day 9 | Uncertainty in prioritizing use cases | Developed a priority matrix to evaluate and rank use cases by importance
Sprint3 | Day 12 | Challenges debugging Python practice code | Independently debugged and resolved code issues
Sprint4 | Day 13 | SQL queries taking longer than expected | Optimized queries with guidance from mentor
Sprint5 | Day 23 | Challenges integrating voice processing with workflows | Scheduled and conducted debugging session to resolve integration issues

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 23rd Sep | 7th Oct | Clarify requirements at the start | Assuming requirements are clear | Reviewing project objectives | Held detailed discussion with mentor to clarify requirements
2 | Sprint 2 | 8th Oct | 22nd Oct | Document workflow steps early | Working without a plan | Brainstorming ideas | Conducted brainstorming session and reviewed project objectives
3 | Sprint 4 | 23ed oct | 6th Nov | Research missing information | Ignoring incomplete info | Prioritizing tasks | Performed research and consulted resources to fill gaps
4 | sprint 5 | 6th Nov | 20th Nov | Debug code independently | Waiting too long to fix issues | Practicing Python coding | Independently debugged and resolved Python code issues